## Slide 1: CS 2212B
Introduction to Software Engineering
Kostas Kontogiannis
Lecture 17: Life Cycle Models – Cost Estimation

## Slide 2: Software Life-Cycle Models
Life-cycle model (also, process model)
The software development and operation activities and their ordering
  Requirements elicitation
  Specification
  Design
  Implementation
  Integration
  Maintenance phase
  Retirement
  …

## Slide 3: Waterfall Model
Characterized by
  Sequential steps (phases)
  Feedback loops (between two phases in development)
  Documentation-driven
Advantages
  Documentation
  Maintenance easier
Disadvantages
  Complete and frozen specification document up-front often not feasible in practice
  Customer involvement in the first phase only
  Sequential and complete execution of phases often not desirable
  Process difficult to control
  The product becomes available very late in the process

## Slide 4: Incremental
Design
Coding
Test
Deployment
Design
Coding
Test
Deployment
Design
Coding
Test
Deployment
Requirements
Release 1
Release 2
Release 3
Each release adds more functionality, i.e., a new increment
(Some call it iterative)

## Slide 5: Evolutionary
Design
Coding
Test
Deployment
Requirements
Design
Coding
Test
Deployment
Requirements
Design
Coding
Test
Deployment
Requirements
Feedback
Version 1
Version 2
Version 3
New versions implement new and evolving requirements
(Some call it iterative)

## Slide 6: Spiral model

## Slide 7: The four variables of a Project
The main four variables of a project
  Development cost
  Time
  Quality
  Scope
Development cost, time and quality are bad control variables
  The number of developers can only be incrementally increased (negative effects beyond the optimal count)
  Deadlines are often predetermined externally (e.g., market window, important presentation)
  Low quality upsets customers and developers
Scope is the only real control variable

## Slide 8: Function Points
The idea of function point was first proposed by Albrecht in 1979.
The function point of a system is a measure of the “functionality” of the system.
Steps
  Counting the information domain – counting FPs
  Assessing complexity of the software – adjusting FPs
  Applying an empirical relationship to come up with LOC or P-months based on the adjusted FPs
This method cannot be performed automatically
©Ian Sommerville 1995

## Slide 9: Counting Function Points

## Slide 10: Counting Function Points
User inputs. Each user input that provides distinct application oriented data to the software is counted.
User outputs. Each user output that provides application oriented information to the user is counted. Individual data items within a report are not counted separately.
User inquiries. This is an on-line input that results in the generation of some response.
Files. Each master file is counted.
External interfaces. Each interface that is used to transmit information to another system is counted.

## Slide 11: Adjusting Function Points
Answer the following questions using a scale of [0-5]: 0 not important; 5 absolutely essential. We call them influence factors (Fi).
1. Does the system require reliable backup and recovery?
2. Are data communications required?
3. Are there distributed processing functions?
4. Is performance critical?
5. Will the system run in an existing, heavily utilized operational env.?
6. Does the system require on-line data entry?

## Slide 12: Adjusting Function Points
7. Does the on-line data entry require the input transaction to be built over multiple screens or operations (user efficiency)?
8. Are the master files updated on-line?
9. Are the inputs, outputs, files, or inquiries complex?
10. Is the internal processing complex?
11. Is the code designed to be reusable?
12. Is installation included in the design?
13. Is the system designed for multiple installations?
14. Is the application designed to facilitate change and ease of use by the user?

## Slide 13: Map FPs to LOC
Use an empirical relationship
  Function point = count total  [0.65 + 0.01  (sum of the 14 Fi)]
  Companies may want to refine their own version
According to a 1989 study, implementing a function point in a given programming language requires the following number of lines of code
  Assembly 320
  C 128
  COBOL 106
  C++ 64
  Visual Basic 32
  SQL 12
See www.ifpug.org for more information on FP

## Slide 14: Example: Project

## Slide 15: Example: Project
Total of FPs = 25
F4 = 4, F10 = 4, other Fi’s are set to 0. Sum of all Fi’s = 8.
FP = 25 x (0.65 + 0.01 x 8) = 18.25
Lines of code in C = 18.25 x 128 LOC = 2336 LOC
In the past, students have implemented their projects using about 2500 LOC.

## Slide 16: Basic COCOMO Formula
Organic mode: PM = 2.4 (KDSI) 1.05
Semi-detached mode: PM = 3 (KDSI) 1.12
Embedded mode: PM = 3.6 (KDSI) 1.2
KDSI = Kilo Delivered Source Instructions
©Ian Sommerville 1995

## Slide 17: COCOMO examples
Organic mode project, 32KLOC
  PM = 2.4 (32) 1.05 = 91 person months
  TDEV = 2.5 (91) 0.38 = 14 months
  N = 91/15 = 6.5 people
Embedded mode project, 128KLOC
  PM = 3.6 (128)1.2 = 1216 person-months
  TDEV = 2.5 (1216)0.32 = 24 months
  N = 1216/24 = 51
©Ian Sommerville 1995